## Sheet 1 - Initial
Initial
Open Story Points | Accomplished SP till now | Hours invested so far | Velocity so far
13 | 0 | 0 | #DIV/0!

## Sheet 1 - Product Burndown
Product Burndown
Sprint | Planned Hours | SP change due to plan change | Accomplished story points in current sprint | Actual Hours | Open Story Points at Begin | Totally Accompl. SP at Begin | Actually accomplished SP at end. | Actual Hours so far at Begin | Open Story Points at End | Velocity (stpts / hour)
2017-04-28 | 7 |  | 0 | 8 | 13 | 0 | 0 | 0 | 13 | 0
2017-05-05 | 7 |  |  | 8 | 13 | 0 | 0 | 8 | 13 | 0
2017-05-12 | 11 |  |  | 6 | 13 | 0 | 0 | 16 | 13 | 0
2017-05-19 | 9 |  | 1 | 7 | 13 | 0 | 1 | 22 | 12 | 0.034483
2017-05-26 | 8 |  |  | 10 | 12 | 1 | 1 | 29 | 11.7241 | 0.034483
2017-06-02 | 7 | 1 |  | 6 | 12.7241 | 1 | 1 | 39 | 12.4828 | 0.034483
2017-06-09 | 4 |  |  | 3 | 12.4828 | 1 | 1 | 45 | 12.3448 | 0.034483
2017-06-16 | 7 |  | 1 | 6 | 12.3448 | 1 | 2 | 48 | 11.3448 | 0.037037
2017-06-23 | 21 |  |  | 15 | 11.3448 | 2 | 2 | 54 | 10.567 | 0.037037
2017-06-30 | 8 |  |  |  | 10.567 | 2 | 2 | 69 | 10.2708 | 0.037037
2017-07-07 | 8 |  |  |  | 10.2708 | 2 | 2 | 69 | 9.9745 | 0.037037
2017-07-14 | 0 |  |  |  | 9.9745 | 2 | 2 | 69 | 9.9745 | 0.037037
2017-07-21 | 0 |  |  |  | 9.9745 | 2 | 2 | 69 | 9.9745 | 0.037037
2017-07-28 | 0 |  |  |  | 9.9745 | 2 | 2 | 69 | 9.9745 | 0.037037
2017-08-04 | 0 |  |  |  | 9.9745 | 2 | 2 | 69 | 9.9745 | 0.037037
2017-08-11 | 0 |  |  |  | 9.9745 | 2 | 2 | 69 | 9.9745 | 0.037037
2017-08-18 | 0 |  |  |  | 9.9745 | 2 | 2 | 69 | 9.9745 | 0.037037
2017-08-25 | 0 |  |  |  | 9.9745 | 2 | 2 | 69 | 9.9745 | 0.037037
2017-09-01 | 0 |  |  |  | 9.9745 | 2 | 2 | 69 | 9.9745 | 0.037037
2017-09-08 | 0 |  |  |  | 9.9745 | 2 | 2 | 69 | 9.9745 | 0.037037
2017-09-15 | 14 |  |  | 9 | 9.9745 | 2 | 2 | 69 | 9.4559 | 0.037037
2017-09-22 | 22 |  |  | 22 | 9.4559 | 2 | 2 | 78 | 8.6411 | 0.037037
2017-09-29 | 8 |  | 3 | 15 | 8.6411 | 2 | 5 | 100 | 5.6411 | 0.043478
2017-10-06 | 12 | 5 |  | 18 | 10.6411 | 5 | 5 | 115 | 10.1194 | 0.043478
2017-10-13 | 15 |  |  | 15 | 10.1194 | 5 | 5 | 133 | 9.4672 | 0.043478
2017-10-20 | 14 |  |  | 12 | 9.4672 | 5 | 5 | 148 | 8.8585 | 0.043478
2017-10-27 | 0 |  |  | 0 | 8.8585 | 5 | 5 | 160 | 8.8585 | 0.043478
2017-11-03 | 0 |  |  | 0 | 8.8585 | 5 | 5 | 160 | 8.8585 | 0.043478
2017-11-10 | 13 |  |  | 11 | 8.8585 | 5 | 5 | 160 | 8.2933 | 0.043478
2017-11-17 | 12 |  |  |  | 8.2933 | 5 | 5 | 171 | 7.7716 | 0.043478
2017-11-24 | 8 |  |  |  | 7.7716 | 5 | 5 | 171 | 7.4237 | 0.043478
2017-12-01 | 8 |  |  |  | 7.4237 | 5 | 5 | 171 | 7.0759 | 0.043478
2017-12-08 | 8 |  |  |  | 7.0759 | 5 | 5 | 171 | 6.7281 | 0.043478
2017-12-15 | 8 |  |  |  | 6.7281 | 5 | 5 | 171 | 6.3803 | 0.043478
2017-12-22 | 0 |  |  |  | 6.3803 | 5 | 5 | 171 | 6.3803 | 0.043478
2017-12-29 | 0 |  |  |  | 6.3803 | 5 | 5 | 171 | 6.3803 | 0.043478
2018-01-05 | 8 |  |  |  | 6.3803 | 5 | 5 | 171 | 6.0324 | 0.043478
2018-01-12 | 8 |  |  |  | 6.0324 | 5 | 5 | 171 | 5.6846 | 0.043478
2018-01-19 | 8 |  |  |  | 5.6846 | 5 | 5 | 171 | 5.3368 | 0.043478
2018-01-26 | 8 |  |  |  | 5.3368 | 5 | 5 | 171 | 4.9889 | 0.043478
2018-02-02 | 8 |  |  |  | 4.9889 | 5 | 5 | 171 | 4.6411 | 0.043478
2018-02-09 | 8 |  |  |  | 4.6411 | 5 | 5 | 171 | 4.2933 | 0.043478
2018-02-16 | 0 |  |  |  | 4.2933 | 5 | 5 | 171 | 4.2933 | 0.043478
2018-02-23 | 8 |  |  |  | 4.2933 | 5 | 5 | 171 | 3.9455 | 0.043478
2018-03-02 | 8 |  |  |  | 3.9455 | 5 | 5 | 171 | 3.5976 | 0.043478
2018-03-09 | 8 |  |  |  | 3.5976 | 5 | 5 | 171 | 3.2498 | 0.043478
2018-03-16 | 8 |  |  |  | 3.2498 | 5 | 5 | 171 | 2.902 | 0.043478
2018-03-23 | 8 |  |  |  | 2.902 | 5 | 5 | 171 | 2.5542 | 0.043478
2018-03-30 | 8 |  |  |  | 2.5542 | 5 | 5 | 171 | 2.2063 | 0.043478
2018-04-06 | 8 |  |  |  | 2.2063 | 5 | 5 | 171 | 1.8585 | 0.043478
| 168 |  | 1.25 | 9.5
Formulas:
Sprint = [Sprint, row above]+7