## Tabellenblatt1
#id | Epic | Description | Priority | Effort | Logic | Design | Tested | Done
<SP5> | Tutor profile | Tutor wants to maintain own profile | 1 | 2 | yes | yes | yes | yes
<SP1> | Admin | Admin wants to administrate data | 2 | 5 | yes | yes | yes | yes
<SP2> | Tutor list | Admin wants to maintain tutoring profiles | 2 | 2 | yes | yes | yes | yes
<SP3> | Review | Admin wants to approve reviews | 2 | 1 | no | no | no | no
<SP7> | Tutor list | User wants to filter tutors | 2 | 2 | yes | yes | yes | yes
<SP8> | Tutor list | User wants to sort tutors | 2 | 1 | yes | no | no | no
<SP9> | Review | User wants to review his tutor | 2 | 3 | no | no | no | no
<SP4> | Tutor profile | Student wants to create tutoring profile | 3 | 3 | yes | yes | yes | yes
<SP6> | Tutor list | User wants to get a list of all tutors | 3 | 5 | yes | yes | yes | yes
<SP10> | Request | User wants to send a tutoring request | 3 | 8 | yes | no | no | no
<SP11> | Log in | User wants to log in | 3 | 3 | yes | yes | yes | yes
<SP12 | Design | User can use website on mobile device | 2 | 5 | yes | yes | yes | yes
<SP13> | Log in | Teachers can log in | 2 | 3 | yes | yes | yes | yes
<SP14> | Administrator | Administrator can see a statistic of all classes, where no student has signed up | 2 | 2 | yes | yes | yes | yes
<SP15> | Administrator | Administrator can accept/reject tutors before they are shown | 3 | 5 | yes | yes | yes | yes
<SP16> | Teachers | Teacher can add comments for tutors who are not accepted yet | 2 | 8 | yes | yes | yes | yes
<SP17> | Contact | Everyone can send wishes/problems to the administrator | 2 | 5 | yes | yes | yes | yes
<SP18> | Images | Tutors can add an image to their profile | 2 | 5 | yes | no | no | no
<SP19> | Comments | Teacher can filter tutors by subject in comment tutor page | 2 | 1 | yes | no | no | no
<SP20> | Emails for admin | Admin can send E-Mails to an outstanding tutor | 2 | 3 | yes | no | no | no