## Sheet 1 - Initial
Initial
Open Story Points | Accomplished SP till now | Hours invested so far | Velocity so far
19 | 1 | 90 | 0.011111

## Sheet 1 - Product Burndown
Product Burndown
Sprint | Planned Hours | SP change due to plan change | Accomplished story points in current sprint | Actual Hours | Open Story Points at Begin | Totally Accompl. SP at Begin | Actually accomplished SP at end. | Actual Hours so far at Begin | Open Story Points at End | Velocity (stpts / hour)
2017-09-11 | 7 |  | 0 | 8 | 19 | 1 | 1 | 90 | 19 | 0.010204
2017-09-18 | 14 |  |  | 9 | 19 | 1 | 1 | 98 | 18.8571 | 0.0093458
2017-09-25 | 22 |  |  | 22 | 18.8571 | 1 | 1 | 107 | 18.6515 | 0.0093458
2017-10-02 | 8 |  | 3 | 15 | 18.6515 | 1 | 4 | 129 | 15.6515 | 0.027778
2017-10-09 | 12 |  |  | 18 | 15.6515 | 4 | 4 | 144 | 15.3182 | 0.027778
2017-10-16 | 15 |  |  | 15 | 15.3182 | 4 | 4 | 162 | 14.9015 | 0.027778
2017-10-23 | 14 |  | 3 | 12 | 14.9015 | 4 | 7 | 177 | 11.9015 | 0.037037
2017-10-30 | 0 |  |  | 0 | 11.9015 | 7 | 7 | 189 | 11.9015 | 0.037037
2017-11-06 | 0 |  |  | 0 | 11.9015 | 7 | 7 | 189 | 11.9015 | 0.037037
2017-11-13 | 13 |  | 0 | 11 | 11.9015 | 7 | 7 | 189 | 11.9015 | 0.035
2017-11-20 | 12 |  |  | 12 | 11.9015 | 7 | 7 | 200 | 11.4815 | 0.035
2017-11-27 | 12 |  |  | 15 | 11.4815 | 7 | 7 | 212 | 11.0615 | 0.035
2017-12-04 | 12 |  | 6 | 12 | 11.0615 | 7 | 13 | 227 | 5.0615 | 0.054393
2017-12-11 | 12 | 2 |  | 12 | 7.0615 | 13 | 13 | 239 | 6.4088 | 0.054393
2017-12-18 | 4 |  |  | 4 | 6.4088 | 13 | 13 | 251 | 6.1912 | 0.054393
2017-12-25 | 0 |  |  |  | 6.1912 | 13 | 13 | 255 | 6.1912 | 0.054393
2018-01-01 | 0 |  |  |  | 6.1912 | 13 | 13 | 255 | 6.1912 | 0.054393
2018-01-08 | 13 |  |  | 13 | 6.1912 | 13 | 13 | 255 | 5.4841 | 0.054393
2018-01-15 | 16 |  |  | 19 | 5.4841 | 13 | 13 | 268 | 4.6138 | 0.054393
2018-01-22 | 12 | 3 | 5 | 13 | 7.6138 | 13 | 18 | 287 | 2.6138 | 0.06
2018-01-29 | 12 |  |  | 12 | 2.6138 | 18 | 18 | 300 | 1.8938 | 0.06
2018-02-05 | 12 |  |  | 3 | 1.8938 | 18 | 18 | 312 | 1.1738 | 0.06
2018-02-12 | 0 |  |  | 0 | 1.1738 | 18 | 18 | 315 | 1.1738 | 0.06
2018-02-19 | 0 |  |  | 0 | 1.1738 | 18 | 18 | 315 | 1.1738 | 0.06
2018-02-26 | 6 |  |  | 5 | 1.1738 | 18 | 18 | 315 | 0.81384 | 0.06
2018-03-05 | 12 |  |  | 12 | 0.81384 | 18 | 18 | 320 | 0.093837 | 0.06
2018-03-12 | 12 |  |  |  | 0.093837 | 18 | 18 | 332 | 0 | 0.06
2018-03-19 | 8 |  |  |  | 0 | 18 | 18 | 332 | 0 | 0.06
2018-03-26 | 0 |  |  |  | 0 | 18 | 18 | 332 | 0 | 0.06
2018-04-02 | 0 |  |  |  | 0 | 18 | 18 | 332 | 0 | 0.06
2018-04-09 | 8 |  |  |  | 0 | 18 | 18 | 332 | 0 | 0.06
2018-04-16 | 8 |  |  |  | 0 | 18 | 18 | 332 | 0 | 0.06
| 78 |  | 2.8333 | 10.0833