## Sheet 1 - Initial
Initial
Open Story Points | Accomplished SP till now | Hours invested so far | Velocity so far
13 | 0 | 0 | #DIV/0!

## Sheet 1 - Product Burndown
Product Burndown
Sprint | Planned Hours | SP change due to plan change | Accomplished story points in current sprint | Actual Hours | Open Story Points at Begin | Totally Accompl. SP at Begin | Actually accomplished SP at end. | Actual Hours so far at Begin | Open Story Points at End | Velocity (stpts / hour)
2017-04-28 | 7 |  | 0 | 8 | 13 | 0 | 0 | 0 | 13 | 0
2017-05-05 | 7 |  |  | 8 | 13 | 0 | 0 | 8 | 13 | 0
2017-05-12 | 11 |  |  | 6 | 13 | 0 | 0 | 16 | 13 | 0
2017-05-19 | 9 |  | 1 | 7 | 13 | 0 | 1 | 22 | 12 | 0.034483
2017-05-26 | 8 |  |  | 10 | 12 | 1 | 1 | 29 | 11.7241 | 0.034483
2017-06-02 | 7 | 1 |  | 6 | 12.7241 | 1 | 1 | 39 | 12.4828 | 0.034483
2017-06-09 | 4 |  |  | 3 | 12.4828 | 1 | 1 | 45 | 12.3448 | 0.034483
2017-06-16 | 7 |  | 1 | 6 | 12.3448 | 1 | 2 | 48 | 11.3448 | 0.037037
2017-06-23 | 21 |  |  | 15 | 11.3448 | 2 | 2 | 54 | 10.567 | 0.037037
2017-06-30 | 8 |  |  |  | 10.567 | 2 | 2 | 69 | 10.2708 | 0.037037
2017-07-07 | 8 |  |  |  | 10.2708 | 2 | 2 | 69 | 9.9745 | 0.037037
2017-07-14 | 0 |  |  |  | 9.9745 | 2 | 2 | 69 | 9.9745 | 0.037037
2017-07-21 | 0 |  |  |  | 9.9745 | 2 | 2 | 69 | 9.9745 | 0.037037
2017-07-28 | 0 |  |  |  | 9.9745 | 2 | 2 | 69 | 9.9745 | 0.037037
2017-08-04 | 0 |  |  |  | 9.9745 | 2 | 2 | 69 | 9.9745 | 0.037037
2017-08-11 | 0 |  |  |  | 9.9745 | 2 | 2 | 69 | 9.9745 | 0.037037
2017-08-18 | 0 |  |  |  | 9.9745 | 2 | 2 | 69 | 9.9745 | 0.037037
2017-08-25 | 0 |  |  |  | 9.9745 | 2 | 2 | 69 | 9.9745 | 0.037037
2017-09-01 | 0 |  |  |  | 9.9745 | 2 | 2 | 69 | 9.9745 | 0.037037
2017-09-08 | 0 |  |  |  | 9.9745 | 2 | 2 | 69 | 9.9745 | 0.037037
2017-09-15 | 14 |  |  | 9 | 9.9745 | 2 | 2 | 69 | 9.4559 | 0.037037
2017-09-22 | 22 |  |  | 22 | 9.4559 | 2 | 2 | 78 | 8.6411 | 0.037037
2017-09-29 | 8 |  | 3 |  | 8.6411 | 2 | 5 | 100 | 8.3448 | 0.037037
2017-10-06 | 12 | 5 |  | 18 | 13.3448 | 5 | 5 | 100 | 12.9004 | 0.037037
2017-10-13 | 15 |  |  | 15 | 12.9004 | 5 | 5 | 118 | 12.3448 | 0.037037
2017-10-20 | 14 |  |  |  | 12.3448 | 5 | 5 | 133 | 11.8263 | 0.037037
2017-10-27 | 8 |  |  |  | 11.8263 | 5 | 5 | 133 | 11.53 | 0.037037
2017-11-03 | 8 |  |  |  | 11.53 | 5 | 5 | 133 | 11.2337 | 0.037037
2017-11-10 | 8 |  |  |  | 11.2337 | 5 | 5 | 133 | 10.9374 | 0.037037
2017-11-17 | 8 |  |  |  | 10.9374 | 5 | 5 | 133 | 10.6411 | 0.037037
2017-11-24 | 8 |  |  |  | 10.6411 | 5 | 5 | 133 | 10.3448 | 0.037037
2017-12-01 | 8 |  |  |  | 10.3448 | 5 | 5 | 133 | 10.0485 | 0.037037
2017-12-08 | 8 |  |  |  | 10.0485 | 5 | 5 | 133 | 9.7522 | 0.037037
2017-12-15 | 8 |  |  |  | 9.7522 | 5 | 5 | 133 | 9.4559 | 0.037037
2017-12-22 | 8 |  |  |  | 9.4559 | 5 | 5 | 133 | 9.1596 | 0.037037
2017-12-29 | 8 |  |  |  | 9.1596 | 5 | 5 | 133 | 8.8633 | 0.037037
2018-01-05 | 8 |  |  |  | 8.8633 | 5 | 5 | 133 | 8.567 | 0.037037
2018-01-12 | 8 |  |  |  | 8.567 | 5 | 5 | 133 | 8.2708 | 0.037037
2018-01-19 | 8 |  |  |  | 8.2708 | 5 | 5 | 133 | 7.9745 | 0.037037
2018-01-26 | 8 |  |  |  | 7.9745 | 5 | 5 | 133 | 7.6782 | 0.037037
2018-02-02 | 8 |  |  |  | 7.6782 | 5 | 5 | 133 | 7.3819 | 0.037037
2018-02-09 | 8 |  |  |  | 7.3819 | 5 | 5 | 133 | 7.0856 | 0.037037
2018-02-16 | 8 |  |  |  | 7.0856 | 5 | 5 | 133 | 6.7893 | 0.037037
2018-02-23 | 8 |  |  |  | 6.7893 | 5 | 5 | 133 | 6.493 | 0.037037
2018-03-02 | 8 |  |  |  | 6.493 | 5 | 5 | 133 | 6.1967 | 0.037037
2018-03-09 | 8 |  |  |  | 6.1967 | 5 | 5 | 133 | 5.9004 | 0.037037
| 168 |  | 1.25 | 10.2308
Formulas:
Sprint = [Sprint, row above]+7