## Sheet 1 - Initial
Initial
Open Story Points | Accomplished SP till now | Hours invested so far | Velocity so far
12 | 0 | 0 | #DIV/0!

## Sheet 1 - Product Burndown
Product Burndown
Sprint | Planned Hours | SP change due to plan change | Accomplished story points in current sprint | Actual Hours | Open Story Points at Begin | Totally Accompl. SP at Begin | Actually accomplished SP at end. | Actual Hours so far at Begin | Open Story Points at End | Velocity (stpts / hour)
2017-04-28 | 7 |  | 0 | 8 | 12 | 0 | 0 | 0 | 12 | 0
2017-05-05 | 7 |  |  | 8 | 12 | 0 | 0 | 8 | 12 | 0
2017-05-12 | 11 |  |  | 6 | 12 | 0 | 0 | 16 | 12 | 0
2017-05-19 | 9 |  | 1 | 7 | 12 | 0 | 1 | 22 | 11 | 0.034483
2017-05-26 | 8 |  |  | 10 | 11 | 1 | 1 | 29 | 10.7241 | 0.034483
2017-06-02 | 7 | 1 |  | 6 | 11.7241 | 1 | 1 | 39 | 11.4828 | 0.034483
2017-06-09 | 4 |  |  | 3 | 11.4828 | 1 | 1 | 45 | 11.3448 | 0.034483
2017-06-16 | 7 |  | 1 | 6 | 11.3448 | 1 | 2 | 48 | 10.3448 | 0.037037
2017-06-23 | 21 |  |  | 15 | 10.3448 | 2 | 2 | 54 | 9.567 | 0.037037
2017-06-30 | 8 |  |  |  | 9.567 | 2 | 2 | 69 | 9.2708 | 0.037037
2017-07-07 | 8 |  |  |  | 9.2708 | 2 | 2 | 69 | 8.9745 | 0.037037
2017-07-14 | 0 |  |  |  | 8.9745 | 2 | 2 | 69 | 8.9745 | 0.037037
2017-07-21 | 0 |  |  |  | 8.9745 | 2 | 2 | 69 | 8.9745 | 0.037037
2017-07-28 | 0 |  |  |  | 8.9745 | 2 | 2 | 69 | 8.9745 | 0.037037
2017-08-04 | 0 |  |  |  | 8.9745 | 2 | 2 | 69 | 8.9745 | 0.037037
2017-08-11 | 0 |  |  |  | 8.9745 | 2 | 2 | 69 | 8.9745 | 0.037037
2017-08-18 | 0 |  |  |  | 8.9745 | 2 | 2 | 69 | 8.9745 | 0.037037
2017-08-25 | 0 |  |  |  | 8.9745 | 2 | 2 | 69 | 8.9745 | 0.037037
2017-09-01 | 0 |  |  |  | 8.9745 | 2 | 2 | 69 | 8.9745 | 0.037037
2017-09-08 | 0 |  |  |  | 8.9745 | 2 | 2 | 69 | 8.9745 | 0.037037
2017-09-15 | 14 |  |  |  | 8.9745 | 2 | 2 | 69 | 8.4559 | 0.037037
2017-09-22 | 8 |  |  |  | 8.4559 | 2 | 2 | 69 | 8.1596 | 0.037037
2017-09-29 | 8 |  |  |  | 8.1596 | 2 | 2 | 69 | 7.8633 | 0.037037
2017-10-06 | 8 |  |  |  | 7.8633 | 2 | 2 | 69 | 7.567 | 0.037037
2017-10-13 | 8 |  |  |  | 7.567 | 2 | 2 | 69 | 7.2708 | 0.037037
2017-10-20 | 8 |  |  |  | 7.2708 | 2 | 2 | 69 | 6.9745 | 0.037037
2017-10-27 | 8 |  |  |  | 6.9745 | 2 | 2 | 69 | 6.6782 | 0.037037
2017-11-03 | 8 |  |  |  | 6.6782 | 2 | 2 | 69 | 6.3819 | 0.037037
2017-11-10 | 8 |  |  |  | 6.3819 | 2 | 2 | 69 | 6.0856 | 0.037037
2017-11-17 | 8 |  |  |  | 6.0856 | 2 | 2 | 69 | 5.7893 | 0.037037
2017-11-24 | 8 |  |  |  | 5.7893 | 2 | 2 | 69 | 5.493 | 0.037037
2017-12-01 | 8 |  |  |  | 5.493 | 2 | 2 | 69 | 5.1967 | 0.037037
2017-12-08 | 8 |  |  |  | 5.1967 | 2 | 2 | 69 | 4.9004 | 0.037037
2017-12-15 | 8 |  |  |  | 4.9004 | 2 | 2 | 69 | 4.6041 | 0.037037
2017-12-22 | 8 |  |  |  | 4.6041 | 2 | 2 | 69 | 4.3078 | 0.037037
2017-12-29 | 8 |  |  |  | 4.3078 | 2 | 2 | 69 | 4.0115 | 0.037037
2018-01-05 | 8 |  |  |  | 4.0115 | 2 | 2 | 69 | 3.7152 | 0.037037
2018-01-12 | 8 |  |  |  | 3.7152 | 2 | 2 | 69 | 3.4189 | 0.037037
2018-01-19 | 8 |  |  |  | 3.4189 | 2 | 2 | 69 | 3.1226 | 0.037037
2018-01-26 | 8 |  |  |  | 3.1226 | 2 | 2 | 69 | 2.8263 | 0.037037
2018-02-02 | 8 |  |  |  | 2.8263 | 2 | 2 | 69 | 2.53 | 0.037037
2018-02-09 | 8 |  |  |  | 2.53 | 2 | 2 | 69 | 2.2337 | 0.037037
2018-02-16 | 8 |  |  |  | 2.2337 | 2 | 2 | 69 | 1.9374 | 0.037037
2018-02-23 | 8 |  |  |  | 1.9374 | 2 | 2 | 69 | 1.6411 | 0.037037
2018-03-02 | 8 |  |  |  | 1.6411 | 2 | 2 | 69 | 1.3448 | 0.037037
2018-03-09 | 8 |  |  |  | 1.3448 | 2 | 2 | 69 | 1.0485 | 0.037037
| 143 |  | 0.66667 | 7.6667
Formulas:
Sprint = [Sprint, row above]+7