## Summary
Sprint Log
SprintNr | Goal
2017-05-02 | Login
2017-05-09 | Login
16.05.20117 | Login
23.05.1017 | Tutor list
2017-05-30 | Tutor list
2017-06-06 | Tutor list
2017-06-13 | Tutor list
2017-06-20 | Tutor list
2017-09-15 | Tutor list

## 2017.05.02
User Story | Task | Initial Estimation | Current Estimation | Worked | Remain | Name | Planned hours
Login | [5 empty] | Eva | 4
| Sperre zum Home Bereich einrichten | 3 | 3 | 4 | -1 | Danijal | 3
7
Tutor List | Design erstellen | 3 | 3 | 4 | -1
| Logout Button | 1 | 1 | 0 | 1
|  | 7 | 7 | 8 | -1

## 2017.05.09
User Story | Task | Initial Estimation | Current Estimation | Worked | Remain | Name | Planned hours
Login | [5 empty] | Eva | 4
| Sessions einrichten | 3 | 3 | 1 | 2 | Danijal | 7
11
Tutor profile | Design erstellen | 5 | 5 | 3 | 2
Tutor list | Design erstellen |  |  | 2
|  | 8 | 8 | 6 | 4

## 2017.05.16
User Story | Task | Initial Estimation | Current Estimation | Worked | Remain | Name | Planned hours
Login | [5 empty] | Eva | 4
| Sessions einrichten | 3 | 1 | 1 | 0 | Danijal | 5
Liste anzeigen | UOW einrichten | 2 | 2 | 2 |  |  | 9
Tutor profile | Foto hochladen | 3 | 3 | 1 | 2
0
Tutor list | Design bearbeiten | 3 | 3 | 1 | 2
Login | Design bearbeiten | 2 | 2 | 2 | 0
0
0
0
0
0
0
0
0
0
0
|  | 13 | 11 | 7 | 4

## 2017.05.23
User Story | Task | Initial Estimation | Current Estimation | Worked | Remain | Name | Planned hours
Liste sortieren | Programmieren | 1 | 1 | 4 | -3 | Eva | 3
Liste filtern | Programmieren | 2 | 2 | 0 | 2 | Danijal | 5
[5 empty] | 0 |  | 8
0
Tutor list | Liste anzeigen | 5 | 5 | 6 | -1
0
0
0
0
0
0
0
0
0
0
0
0
0
|  | 8 | 8 | 10 | -2

## 2017.05.30
User Story | Task | Initial Estimation | Current Estimation | Worked | Remain | Name | Planned hours
Liste sortieren | Programmieren | 1 | 1 | 2 | -1 | Eva | 4
Liste filtern | Programmieren | 3 | 3 | 1 | 2 | Danijal | 3
[5 empty] | 0 |  | 7
0
Tutor list | Bilder in Liste anzeigen | 3 | 3 | 3 | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
|  | 7 | 7 | 6 | 1

## 2017.06.06
User Story | Task | Initial Estimation | Current Estimation | Worked | Remain
Liste filtern | Programmieren | 2 | 2 | 0 | 2
Liste sortieren | Reviews verknüpfen | 1 | 1 | 1 | 0
0
Tutor list | Bilder in Liste anzeigen | 2 | 2 | 2 | 0
0
0
|  | 5 | 5 | 3 | 2
Name | Planned hours
Eva | 2
Danijal | 2
4

## 2017.06.13
User Story | Task | Initial Estimation | Current Estimation | Worked | Remain
Liste sortieren | nach Reviews sortieren | 2 | 2 | 2 | 0
Klick auf Tutor |  | 1 | 1 | 1 | 0
0
Tutor list | Bilder in Liste anzeigen | 3 | 3 | 3 | 0
Liste sortieren | Design | 1 | 1 | 0 | 1
0
|  | 7 | 7 | 6 | 1
Name | Planned hours
Eva | 3
Danijal | 4
7

## 2017.06.20
User Story | Task | Initial Estimation | Current Estimation | Worked | Remain
Admin | Accept/Reject Reviews | 5 | 5 | 8 | -3
Admin | Change Masterdata | 5 | 5 | 7 | -2
Admin | Maintain Tutoring profiles | 8 | 8 |  | 8
Tutor list | Bilder in Liste anzeigen | 3 | 3 | 0 | 3
0
|  | 21 | 21 | 15 | 6
Name | Planned hours
Eva | 18
Danijal | 3
21

## 2017.09.15
User Story | Task | Initial Estimation | Current Estimation | Worked | Remain
Tutor | Create tutoring profile | 5 | 5 | 3 | 2
| maintain tutoring profile | 3 | 3
Tutor list | Design | 6 | 3 | 0 | 3
|  | 14 | 11 | 3 | 5
Name | Planned hours
Eva | 8
Danijal | 6
14