## Sheet 1 - Initial
Initial
Open Story Points | Accomplished SP till now | Hours invested so far | Velocity so far
12 | 0 | 0 | #DIV/0!

## Sheet 1 - Product Burndown
Product Burndown
Sprint | Planned Hours | SP change due to plan change | Accomplished story points in current sprint | Actual Hours | Open Story Points at Begin | Totally Accompl. SP at Begin | Actually accomplished SP at end. | Actual Hours so far at Begin | Open Story Points at End | Velocity (stpts / hour)
2017-04-28 | 7 |  | 0 | 8 | 12 | 0 | 0 | 0 | 12 | 0
2017-05-05 | 8 |  |  | 7 | 12 | 0 | 0 | 8 | 12 | 0
2017-05-12 | 11 |  |  | 6 | 12 | 0 | 0 | 15 | 12 | 0
2017-05-19 | 9 |  | 1 | 7 | 12 | 0 | 1 | 21 | 11 | 0.035714
2017-05-26 | 8 |  |  |  | 11 | 1 | 1 | 28 | 10.7143 | 0.035714
2017-06-02 | 8 |  |  |  | 10.7143 | 1 | 1 | 28 | 10.4286 | 0.035714
2017-06-09 | 8 |  |  |  | 10.4286 | 1 | 1 | 28 | 10.1429 | 0.035714
2017-06-16 | 8 |  |  |  | 10.1429 | 1 | 1 | 28 | 9.8571 | 0.035714
2017-06-23 | 8 |  |  |  | 9.8571 | 1 | 1 | 28 | 9.5714 | 0.035714
2017-06-30 | 8 |  |  |  | 9.5714 | 1 | 1 | 28 | 9.2857 | 0.035714
2017-07-07 | 8 |  |  |  | 9.2857 | 1 | 1 | 28 | 9 | 0.035714
2017-07-14 | 0 |  |  |  | 9 | 1 | 1 | 28 | 9 | 0.035714
2017-07-21 | 0 |  |  |  | 9 | 1 | 1 | 28 | 9 | 0.035714
2017-07-28 | 0 |  |  |  | 9 | 1 | 1 | 28 | 9 | 0.035714
2017-08-04 | 0 |  |  |  | 9 | 1 | 1 | 28 | 9 | 0.035714
2017-08-11 | 0 |  |  |  | 9 | 1 | 1 | 28 | 9 | 0.035714
2017-08-18 | 0 |  |  |  | 9 | 1 | 1 | 28 | 9 | 0.035714
2017-08-25 | 0 |  |  |  | 9 | 1 | 1 | 28 | 9 | 0.035714
2017-09-01 | 0 |  |  |  | 9 | 1 | 1 | 28 | 9 | 0.035714
2017-09-08 | 0 |  |  |  | 9 | 1 | 1 | 28 | 9 | 0.035714
2017-09-15 | 8 |  |  |  | 9 | 1 | 1 | 28 | 8.7143 | 0.035714
2017-09-22 | 8 |  |  |  | 8.7143 | 1 | 1 | 28 | 8.4286 | 0.035714
2017-09-29 | 8 |  |  |  | 8.4286 | 1 | 1 | 28 | 8.1429 | 0.035714
2017-10-06 | 8 |  |  |  | 8.1429 | 1 | 1 | 28 | 7.8571 | 0.035714
2017-10-13 | 8 |  |  |  | 7.8571 | 1 | 1 | 28 | 7.5714 | 0.035714
2017-10-20 | 8 |  |  |  | 7.5714 | 1 | 1 | 28 | 7.2857 | 0.035714
2017-10-27 | 8 |  |  |  | 7.2857 | 1 | 1 | 28 | 7 | 0.035714
2017-11-03 | 8 |  |  |  | 7 | 1 | 1 | 28 | 6.7143 | 0.035714
2017-11-10 | 8 |  |  |  | 6.7143 | 1 | 1 | 28 | 6.4286 | 0.035714
2017-11-17 | 8 |  |  |  | 6.4286 | 1 | 1 | 28 | 6.1429 | 0.035714
2017-11-24 | 8 |  |  |  | 6.1429 | 1 | 1 | 28 | 5.8571 | 0.035714
2017-12-01 | 8 |  |  |  | 5.8571 | 1 | 1 | 28 | 5.5714 | 0.035714
2017-12-08 | 8 |  |  |  | 5.5714 | 1 | 1 | 28 | 5.2857 | 0.035714
2017-12-15 | 8 |  |  |  | 5.2857 | 1 | 1 | 28 | 5 | 0.035714
2017-12-22 | 8 |  |  |  | 5 | 1 | 1 | 28 | 4.7143 | 0.035714
2017-12-29 | 8 |  |  |  | 4.7143 | 1 | 1 | 28 | 4.4286 | 0.035714
2018-01-05 | 8 |  |  |  | 4.4286 | 1 | 1 | 28 | 4.1429 | 0.035714
2018-01-12 | 8 |  |  |  | 4.1429 | 1 | 1 | 28 | 3.8571 | 0.035714
2018-01-19 | 8 |  |  |  | 3.8571 | 1 | 1 | 28 | 3.5714 | 0.035714
2018-01-26 | 8 |  |  |  | 3.5714 | 1 | 1 | 28 | 3.2857 | 0.035714
2018-02-02 | 8 |  |  |  | 3.2857 | 1 | 1 | 28 | 3 | 0.035714
2018-02-09 | 8 |  |  |  | 3 | 1 | 1 | 28 | 2.7143 | 0.035714
2018-02-16 | 8 |  |  |  | 2.7143 | 1 | 1 | 28 | 2.4286 | 0.035714
2018-02-23 | 8 |  |  |  | 2.4286 | 1 | 1 | 28 | 2.1429 | 0.035714
2018-03-02 | 8 |  |  |  | 2.1429 | 1 | 1 | 28 | 1.8571 | 0.035714
2018-03-09 | 8 |  |  |  | 1.8571 | 1 | 1 | 28 | 1.5714 | 0.035714
| 131 |  | 0.5 | 7
Formulas:
Sprint = [Sprint, row above]+7