## Summary
Sprint Log
SprintNr | Goal
2017-05-02 | Login
2017-05-09 | Login
16.05.20117 | Login
23.05.1017 | Tutor list
2017-05-30 | Tutor list
2017-06-06 | Tutor list
2017-06-13 | Tutor list
2017-06-20 | Tutor list
2017-09-15 | Tutor list
2017-09-22 | Tutor list
2017-09-29 | -
2017-10-06 | Bugs
2017-10-17 | Statistics
2017-10-24 | Comments
2017-11-14 | Comments
2017-11-21 | Bugs/Delete tutor afterwards
2017-11-28 | Testing, Design
2017-12-05 | Release
2017-12-12 | Tutoring request, images
2017-12-19 | Admin mail, filter
2018-01-10 | Images, sort
2018-01-16 | Images
2018-01-23 | Release
2018-01-30 | Reviews & Design

## 2017.05.02
User Story | Task | Initial Estimation | Current Estimation | Worked | Remain | Name | Planned hours
Login | [5 empty] | Eva | 4
| Sperre zum Home Bereich einrichten | 3 | 3 | 4 | -1 | Danijal | 3
7
Tutor List | Design erstellen | 3 | 3 | 4 | -1
| Logout Button | 1 | 1 | 0 | 1
|  | 7 | 7 | 8 | -1

## 2017.05.09
User Story | Task | Initial Estimation | Current Estimation | Worked | Remain | Name | Planned hours
Login | [5 empty] | Eva | 4
| Sessions einrichten | 3 | 3 | 1 | 2 | Danijal | 7
11
Tutor profile | Design erstellen | 5 | 5 | 3 | 2
Tutor list | Design erstellen |  |  | 2
|  | 8 | 8 | 6 | 4

## 2017.05.16
User Story | Task | Initial Estimation | Current Estimation | Worked | Remain | Name | Planned hours
Login | [5 empty] | Eva | 4
| Sessions einrichten | 3 | 1 | 1 | 0 | Danijal | 5
Liste anzeigen | UOW einrichten | 2 | 2 | 2 |  |  | 9
Tutor profile | Foto hochladen | 3 | 3 | 1 | 2
0
Tutor list | Design bearbeiten | 3 | 3 | 1 | 2
Login | Design bearbeiten | 2 | 2 | 2 | 0
0
0
0
0
0
0
0
0
0
0
|  | 13 | 11 | 7 | 4

## 2017.05.23
User Story | Task | Initial Estimation | Current Estimation | Worked | Remain | Name | Planned hours
Liste sortieren | Programmieren | 1 | 1 | 4 | -3 | Eva | 3
Liste filtern | Programmieren | 2 | 2 | 0 | 2 | Danijal | 5
[5 empty] | 0 |  | 8
0
Tutor list | Liste anzeigen | 5 | 5 | 6 | -1
0
0
0
0
0
0
0
0
0
0
0
0
0
|  | 8 | 8 | 10 | -2

## 2017.05.30
User Story | Task | Initial Estimation | Current Estimation | Worked | Remain | Name | Planned hours
Liste sortieren | Programmieren | 1 | 1 | 2 | -1 | Eva | 4
Liste filtern | Programmieren | 3 | 3 | 1 | 2 | Danijal | 3
[5 empty] | 0 |  | 7
0
Tutor list | Bilder in Liste anzeigen | 3 | 3 | 3 | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
|  | 7 | 7 | 6 | 1

## 2017.06.06
User Story | Task | Initial Estimation | Current Estimation | Worked | Remain
Liste filtern | Programmieren | 2 | 2 | 0 | 2
Liste sortieren | Reviews verknüpfen | 1 | 1 | 1 | 0
0
Tutor list | Bilder in Liste anzeigen | 2 | 2 | 2 | 0
0
0
|  | 5 | 5 | 3 | 2
Name | Planned hours
Eva | 2
Danijal | 2
4

## 2017.06.13
User Story | Task | Initial Estimation | Current Estimation | Worked | Remain
Liste sortieren | nach Reviews sortieren | 2 | 2 | 2 | 0
Klick auf Tutor |  | 1 | 1 | 1 | 0
0
Tutor list | Bilder in Liste anzeigen | 3 | 3 | 3 | 0
Liste sortieren | Design | 1 | 1 | 0 | 1
0
|  | 7 | 7 | 6 | 1
Name | Planned hours
Eva | 3
Danijal | 4
7

## 2017.06.20
User Story | Task | Initial Estimation | Current Estimation | Worked | Remain
Admin | Accept/Reject Reviews | 5 | 5 | 8 | -3
Admin | Change Masterdata | 5 | 5 | 7 | -2
Admin | Maintain Tutoring profiles | 8 | 8 |  | 8
Tutor list | Bilder in Liste anzeigen | 3 | 3 | 0 | 3
0
|  | 21 | 21 | 15 | 6
Name | Planned hours
Eva | 18
Danijal | 3
21

## 2017.09.15
User Story | Task | Initial Estimation | Current Estimation | Worked | Remain
Tutor | Create tutoring profile | 5 | 5 | 3 | 2
| maintain tutoring profile | 3 | 3 | 3
| Login | 1 | 1 | 1
| Filter | 1 | 1 | 1
Tutor list | Design | 6 | 3 | 1 | 2
|  | 16 | 13 | 9 | 4
Name | Planned hours
Eva | 8
Danijal | 6
14

## 2017.09.22
User Story | Task | Initial Estimation | Current Estimation | Worked | Remain
Tutor | Edit Tutors | 2 | 2 |  | 2
| Testing | 5 | 5 |  | 5
All | Design | 15 | 15 | 20 | -5
|  | 22 | 22 | 20 | 2
Name | Planned hours
Eva | 7
Danijal | 15
22

## 2017.10.06
User Story | Task | Initial Estimation | Current Estimation | Worked | Remain
All
| Model Change + bugs | 6 | 6 | 6 | 0
All | Design responsive | 6 | 6 | 12 | -6
|  | 12 | 12 | 18 | -6
Name | Planned hours
Eva | 6
Danijal | 6
12

## 2017.17.10
User Story | Task | Initial Estimation | Current Estimation | Worked | Remain
All
| Model Change | 1 | 1 | 1 | 0
| Statistics | 2 | 2 | 2 | 0
| Tutor accept | 4 | 4 | 4 | 0
All | Design responsive | 8 | 8 | 8 | 0
|  | 15 | 15 | 15 | 0
Name | Planned hours
Eva | 7
Danijal | 8
15

## 2017.24.10
User Story | Task | Initial Estimation | Current Estimation | Worked | Remain
All
| Comments for teachers | 6 | 6 | 4 | 2
All | Design responsive | 8 | 8 | 8 | 0
|  | 14 | 14 | 12 | 2
Name | Planned hours
Eva | 6
Danijal | 8
14

## 2017.14.11
User Story | Task | Initial Estimation | Current Estimation | Worked | Remain
All
| Comments for teachers | 6 | 6 | 6 | 0
All | Login time issues, design responsive | 7 | 7 | 5 | 2
|  | 13 | 13 | 11 | 2
Name | Planned hours
Eva | 6
Danijal | 7
13

## 2017.21.11
User Story | Task | Initial Estimation | Current Estimation | Worked | Remain
All
| Accept/Reject tutor (Role refreshing issues) | 6 | 6 | 3 | 3
| Delete Tutor afterwards | 6 | 6 | 3 | 3
All | Contact | 3 | 3 | 3 | 0
| Design | 3 | 3 | 3 | 0
|  | 18 | 18 | 12 | 6
Name | Planned hours
Eva | 6
Danijal | 6
12

## 2017.28.11
User Story | Task | Initial Estimation | Current Estimation | Worked | Remain
All
| Testing and Planning | 6 | 6 | 6 | 0
All | Contact | 3 | 3 | 3 | 0
| Design | 3 | 3 | 6 | -3
|  | 12 | 12 | 15 | -3
Name | Planned hours
Eva | 6
Danijal | 6
12

## 2017.05.12
User Story | Task | Initial Estimation | Current Estimation | Worked | Remain
All
| Release and planning | 6 | 6 | 6 | 0
All | Planning | 4 | 4 | 4 | 0
| Design | 2 | 2 | 2 | 0
|  | 12 | 12 | 12 | 0
Name | Planned hours
Eva | 6
Danijal | 6
12

## 2017.12.12
User Story | Task | Initial Estimation | Current Estimation | Worked | Remain
All
| Tutoring request | 5 | 5 | 5 | 0
| Filter tutors in comment page by subject | 1 | 1 | 1
All | Images for tutors | 4 | 4 | 4 | 0
| Design | 2 | 2 | 2 | 0
|  | 12 | 12 | 12 | 0
Name | Planned hours
Eva | 6
Danijal | 6
12

## 2017.19.12
User Story | Task | Initial Estimation | Current Estimation | Worked | Remain
All
| Filter bug | 1 | 1 | 1 | 0
| Filter tutors in comment page by subject | 1 | 1 | 1
All | Admin mail | 2 | 2 | 2 | 0
|  | 4 | 4 | 4 | 0
Name | Planned hours
Eva | 2
Danijal | 2
4

## 2018.10.01
User Story | Task | Initial Estimation | Current Estimation | Worked | Remain
All
| Sort tutors | 5 | 5 | 5 | 0
All | Images | 7 | 7 | 6 | 1
| Admin mail | 1 | 1 | 2 | -1
|  | 13 | 13 | 13 | 0
Name | Planned hours
Eva | 5
Danijal | 8
13

## 2018.16.01
User Story | Task | Initial Estimation | Current Estimation | Worked | Remain
All
| Release Docs | 2 | 2 | 2 | 0
| Bugs | 4 | 4 | 0 | 4
| Images | 0 | 0 | 10
All | Images | 8 | 8 | 2 | 6
| Testing | 2 | 2 | 0 | 2
| Design | 0 | 0 | 5
|  | 16 | 16 | 19 | 12
Name | Planned hours
Eva | 6
Danijal | 10
16

## 2018.23.01
User Story | Task | Initial Estimation | Current Estimation | Worked | Remain
All
| Release & Planning | 4 | 4 | 5 | -1
| Bugs | 2 | 4 | 1 | 3
All | Design | 6 | 6 | 5 | 1
| Bug fixes | 2 | 2 | 2 | 2
|  | 14 | 16 | 13 | 5
Name | Planned hours
Eva | 6
Danijal | 6
12

## 2018.30.01
User Story | Task | Initial Estimation | Current Estimation | Worked | Remain
All
| Reviews & Review accept | 4 | 4 | 4 | 0
| Bugs | 2 | 2 | 2 | 0
0
0
All | Design | 3 | 3 | 3 | 0
| Different images | 3 | 3 | 3 | 0
0
0
|  | 12 | 12 | 12 | 0
Name | Planned hours
Eva | 6
Danijal | 6
12

## 2018.06.02
User Story | Task | Initial Estimation | Current Estimation | Worked | Remain
All
| Reviews & Review accept | 4 | 4 | 0 | 4 | (krank)
| Bugs | 2 | 2 | 0 | 2
0
0
All | Design | 6 | 6 | 3 | 3
0
0
0
|  | 12 | 12 | 3 | 9
Name | Planned hours
Eva | 6
Danijal | 6
12

## Tabelle2
User Story | Task | Initial Estimation | Current Estimation | Worked | Remain
All
| Reviews & Statistics | 3 | 3 | 0 | 3
0
0
All | Design | 3 | 3 | 0 | 3
0
0
0
|  | 6 | 6 | 0 | 6
Name | Planned hours
Eva | 3
Danijal | 3
6